## Tester Tracker
SpotLift — Google Play Closed Test Tracker
Goal | 12 active testers | Test length | 14 consecutive days | Target platform | Android + Google account | Start date |  | Earliest eligible date |  | Opted in | 0 | Installed | 0
Tester # | Name | Best Contact | Contact Method | Google Account Email | Android Device | Recruited At | Opted In? | Installed? | Opt-in Date | Day-14 Date | Day-14 Complete? | Feedback Received? | Notes / Follow-up
1 | [6 empty] | No | No |  |  | No | No | Required tester
2 | [6 empty] | No | No |  |  | No | No | Required tester
3 | [6 empty] | No | No |  |  | No | No | Required tester
4 | [6 empty] | No | No |  |  | No | No | Required tester
5 | [6 empty] | No | No |  |  | No | No | Required tester
6 | [6 empty] | No | No |  |  | No | No | Required tester
7 | [6 empty] | No | No |  |  | No | No | Required tester
8 | [6 empty] | No | No |  |  | No | No | Required tester
9 | [6 empty] | No | No |  |  | No | No | Required tester
10 | [6 empty] | No | No |  |  | No | No | Required tester
11 | [6 empty] | No | No |  |  | No | No | Required tester
12 | [6 empty] | No | No |  |  | No | No | Required tester
13 | [6 empty] | No | No |  |  | No | No | Backup tester
14 | [6 empty] | No | No |  |  | No | No | Backup tester
15 | [6 empty] | No | No |  |  | No | No | Backup tester
Formulas:
Day-14 Complete? = IF(AND([Opted In?]="Yes",TODAY()>=[Day-14 Date]),"Yes","No")

## Recruitment Plan
One Plan: Recruit 15 Gym Testers, Keep 12 Active
Phase | Action | Owner | Timing | Success Check | Notes
1. Prepare | Finish Play Console setup and publish the closed-testing release. | Founder | Before recruiting | Opt-in link works on an Android phone | Do one install yourself first.
2. Recruit | Approach Android users at your gym and ask for a 14-day beta test. | Founder | 2–3 gym visits | 15 interested testers recorded | Recruit 3 backups because some people will drop.
3. Enroll | Add each tester's Google-account email, then send the Play opt-in link. | Founder | Same day | At least 12 show as opted in | The email must be tied to Google Play on their device.
4. Install | Tester accepts the invitation and installs SpotLift from the closed-test Play link. | Tester | Day 0 | At least 12 installed | They should not use a separately shared APK.
5. Exercise | Ask each tester to scan equipment, search an exercise, and try Coach/weekly planning. | Tester | Days 1–10 | Core flows tried | Short, genuine use is better than passive enrollment.
6. Follow up | Message testers twice and collect one useful note from each. | Founder | Days 4 and 10 | Feedback recorded | Keep everyone opted in for the full period.
7. Apply | After Play confirms 12 testers for 14 consecutive days, apply for production access. | Founder | Day 15+ | Production application enabled | Google reviews the testing answers before production access.
Tester requirements | Android phone or tablet | Google account used in Play Store | Opt in through the test link | Install from Google Play | Remain opted in for 14 days
Recommended pitch | “I built SpotLift to explain gym machines and make workouts easier. Could you test the Android beta for 14 days? It takes about 10 minutes to install and try.”
Incentive idea | Offer a free form walkthrough, coffee/protein shake, or early-feature input—not payment for a positive review.
Important | Do not ask testers to post ratings or reviews during the closed test. Ask for private, honest feedback instead.
Source | Google Play Console requirement shown for this account: 12 opted-in testers for at least 14 days.

## Gym Outreach Script
Gym Recruitment Scripts & Follow-ups
Moment | Suggested wording | What you need | Tracker update
In-person opener | Hey—quick question. I built an Android app called SpotLift that scans gym equipment and explains how to use it. I need a few real gym users to test it for 14 days. Would you be open to trying it? | Android device + Google account | Add name and best contact
If interested | Awesome. I’ll send you a private Google Play test link. You accept it with the Google account on your Android phone, install the app, and try a few gym flows over the next two weeks. | Google-account email | Record email and device
Opt-in message | Here’s the private SpotLift Android beta link: [PASTE OPT-IN LINK]. Open it with the same Google account used in your Play Store, tap Become a tester, then install SpotLift. | Opt-in link | Mark Opted In and date
Day 4 follow-up | How did SpotLift do with the equipment you tried? If anything was confusing or slow, send me one sentence or a screenshot. | Private feedback | Record feedback
Day 10 follow-up | Thanks again for testing SpotLift. Please stay opted in through [DAY-14 DATE]. Is there one feature you’d keep, change, or remove? | Retention through day 14 | Confirm still active
Day 14 thank-you | You made it through the full beta—thank you. Your testing directly helps SpotLift qualify for the Play Store launch. | Thank-you | Mark Day-14 Complete
Tester quick checklist | 1) Open opt-in link 2) Become a tester 3) Install from Play Store 4) Scan one machine 5) Search one exercise 6) Try Coach 7) Stay opted in 14 days
Privacy | Use tester contact information only for this closed test and normal SpotLift follow-up. Do not share the list.
Recruiting target | Recruit 15 people to safely maintain the required 12 active testers.
Best candidates | Regular gym members, trainers, friends, students, or family members who own Android devices and will genuinely install and try the app.